## Instructions
LetCM contract renewal tracker
A decision queue for expiry, notice, internal review, ownership, formal action, and record completion.
How to use this workbook
• Start with active or operationally relevant contracts. One row should represent one current renewal decision population.
• Blue text is user input; black text is formula; orange indicates review or caution.
• Review the synthetic example, then remove it before importing live records.
• Filter by effective review start, effective notice deadline, status, action owner, and overdue action date during a regular review meeting.
• After renewal, extension, replacement, termination, or closure, update the source document and next-term dates instead of carrying forward stale values.
Important boundary
• Formula dates are planning aids. They cannot interpret notice wording, amendments, calendar rules, delivery methods, or jurisdiction-specific requirements.
• The verified/manual notice deadline and review start take precedence over formulas. Preserve the authorised reviewer and source context.
• The tracker does not send formal notice, make a renewal decision, or provide legal advice. Those actions remain with authorised people.
Workbook sheets
• Renewal Tracker: the decision queue, formulas, and review fields.
• Field Guide: the purpose and review rule for each date and action field.

## Renewal Tracker
LetCM contract renewal tracker
Blue text = input. Black text = formula. Verify the current document set and critical dates. The synthetic example row is for demonstration and must be removed before live use.
Contract | Supplier | Contract Owner | Expiry / End Date | Renewal Date (if distinct) | Notice Period (Months) | Calculated Notice Deadline | Verified / Manual Notice Deadline | Effective Notice Deadline | Review Lead Time (Months) | Calculated Review Start | Verified / Manual Review Start | Effective Review Start | Decision Due Date | Renewal Decision | Review Status | Next Action | Action Owner | Action Due Date | Source / Clause Review Note | Date Review State | Document Reference | Notes
SYNTHETIC EXAMPLE — REMOVE | Example Supplier Ltd | Example Owner | 2027-12-31 | 2028-01-01 | 6 |  |  |  | 3 |  |  |  | 2027-05-31 | Review required | Not started | Remove this example and verify source dates. | Example Action Owner | 2027-05-15 | Synthetic only — current agreement and amendments must be reviewed. | Review required | EXAMPLE ONLY — replace with approved source location | All names, values, and dates in this row are synthetic.
Formulas:
Calculated Notice Deadline = IF(OR([Expiry / End Date]="",[Notice Period (Months)]=""),"",EDATE([Expiry / End Date],-[Notice Period (Months)]))
Calculated Review Start = IF(OR([Effective Notice Deadline]="",[Review Lead Time (Months)]=""),"",EDATE([Effective Notice Deadline],-[Review Lead Time (Months)]))

## Field Guide
Field | Class | Purpose | Review rule
Expiry / End Date | Source input | Record the current term end where applicable. | Verify the current executed agreement and amendments.
Renewal Date | Conditional source input | Record the next term start when distinct and known. | Do not infer automatic renewal from the presence of a date.
Notice Period | Source input | Expose the formula input. | Months may not capture every wording; keep source/review note.
Calculated Notice Deadline | Formula | Subtract notice months from expiry for provisional planning. | Never present as verified without document review.
Verified / Manual Notice Deadline | Reviewed input | Override the formula with a reviewed date. | Record who reviewed it and the source.
Effective Notice Deadline | Formula | Use verified/manual date if present, otherwise provisional date. | Use as the working queue date, with review state visible.
Review Lead Time | Process input | Create preparation time before notice. | Choose based on evidence, approvals, alternatives, and transition work.
Calculated / Verified Review Start | Formula + reviewed input | Set internal start and allow a deliberate override. | Internal process dates can be earlier than contractual dates.
Decision Due Date | Process input | Create time for approval and formal action. | Must precede the relevant deadline by enough time to complete action.
Decision / Status | Controlled input | Show current direction and workflow state. | Record uncertainty and exceptions explicitly.
Next Action / Owner / Due | Operational input | Turn the review into accountable work. | No open review should lack a dated next step.
Source / Review State | Required input | Keep date quality and interpretation boundary visible. | Escalate ambiguity rather than guessing.